## Job detail
Time table for coding website |  |  |  |  | Simple |  |  |  | Middle |  |  |  | Difficult |  |  |  | 5% ứng với 1 tuần làm việc
| Progress | Detail | PIC | Job detail | 1-3 year | total | > 3 year | total | 1-3 year | total | > 3 year | total | 1-3 year | total | > 3 year | total
Phase 1 : Making flow | 30% | 10% | ENG user | Study procedure/ actual operation | 2 | 9.5 | 1 | 6.5 | 3 | 12.5 | 3 | 10.5 | 4 | 15 | 4 | 13
|  | 10% | Admin | Meeting & collect requirement from user | 3 |  | 2 |  | 4 |  | 3 |  | 5 |  | 4
|  | 5% | Admin | Making concept system | 4 |  | 3 |  | 5 |  | 4 |  | 5 |  | 4
|  | 5% | Admin+ ADV | Hold meeting & fix concept | 0.5 |  | 0.5 |  | 0.5 |  | 0.5 |  | 1 |  | 1
Phase 2 : Coding | 50% | 10% | ADV | UI/UX design | 2 | 10 | 1.5 | 8 | 3 | 15 | 2 | 12 | 5 | 25 | 3.75 | 20
|  | 10% | ADV | Develop frontend | 2 |  | 1.5 |  | 3 |  | 2 |  | 5 |  | 3.75
|  | 30% | ADV | Develop backend | 6 |  | 5 |  | 9 |  | 8 |  | 15 |  | 12.5
Phase 3 : Testing + Fix bug | 20% | 2% | Admin +ADV | Make test case | 0.5 | 4 | 0.5 | 3.5 | 0.5 | 6 | 0.5 | 5 | 1.25 | 10 | 1.25 | 8.25
|  | 3% | Admin+ ADV | Testing by flow group ->fig bugs | 0.5 |  | 0.5 |  | 1 |  | 1 |  | 1.25 |  | 1.25
|  | 5% | All + ADV | Testing by end_user -> fig bugs | 1 |  | 0.5 |  | 1.5 |  | 1 |  | 2.5 |  | 1.25
|  | 2% | ADV | Deploy website/application | 0.5 |  | 0.5 |  | 0.5 |  | 0.5 |  | 1.25 |  | 1.25
|  | 3% | ADV | Make manual + Launching system | 0.5 |  | 0.5 |  | 1 |  | 1 |  | 1.25 |  | 1.25
|  | 5% | ADV | Fix bugs after launching | 1 |  | 1 |  | 1.5 |  | 1 |  | 2.5 |  | 2
Phase Maintain | base on each project |  | Admin | Meeting & review to improve system
|  |  | ADV | Modify code
|  |  | ADV | Test new function after modify
|  |  | ADV | Launching new version
|  |  |  | total time/week | 23.5 | 14 | 18 | 11.5 | 33.5 | 21 | 27.5 | 17 | 50 | 35 | 41.25 | 28.25
|  |  |  | total time/month | 5.875 | code | 4.5 | code | 8.375 | code | 6.875 | code | 12.5 | code | 10.3125 | code
[9 empty] | increase 1.5 times |  |  |  | increase 2.5 times

## Time table job
CODING WEBSITE GENERAL PLAN
|  | 30% |  | 50% | 10% | 10%
I. ENG User
II. Admin
1. DC DRW checking and problem feedback
2. MP problem feedback
III. ADV
IV. All
Coding
Testing
Fix bugs
DE DRW issue
ADV start coding
2week
Test
final request
C-BOM analysis
Code finish
Assy Flow
~ 2.5 months
~ 2 months
~ 1.5 week
Function Inspection making
2 week
ASSY ST calculation(PIA)
ST Balance
1 month
1 weeks
JKK Inspection method analysis
DC problem analys
4weeks
C-BOM Sharing
Transfer to Launching project
UI making
PCB process analysis
ASSY proces analysis
1st feedback
QBOP analysis
JKK analysis
PCB process analysis
ASSY proces analysis
2nd feedback
inspection method
final feedback
DE DRW checking
DE problem feedback
PIC: Project team
Together with: ASSY/PQA/PE
Concept system & target
(...)
2nd Assy Flow
1. Simple project
2. Middle project
3. Difficult project
* Standard time balance
*Packing/ kitting
Unit funciton analysis
Checker ST calculation(PIA)
1 week
* ST target
* Base on PFi1 standard
Making flow
try to input in DE phase
Problem feedback
4. Accuracy guaranted C-BOM
Process/ Unit flow list making
DC DRW/ Unit flow analysis
DE DRW/ Unit flow analysis
Proces flow update
Guarantee point summarize
1st ver
3 week
Auto/ MIP support analysis
Confirm all DC problem feedback are changed in DE or not?
new DE problem study
PIA and PUR :
Maker survey
HNS/FFC layoyt checing
Design change request for layout
Temp layout idea
Temp layout for transportation
Actual DE machine ETA
2week
1week
3week
Checker Map
Maintain (if need)
Making flow for kaizen point
UX making